## Sheet1
Week Of | MON | TUE | WED | THU | FRI | SAT | SUN
2019-02-04 | DESIGN SPEC (TOP LEVEL) | [6 empty] | Week Of | Task Completed
2019-02-11 | DESIGN SPEC (LOW LEVEL) | [6 empty] | 2019-02-04 | Design Specifications
2019-02-18 | Receive ST board and setup software | Created GIT | Play with examples | Edited Template |  | Testing Array Code (ARDUINO) |  | 2019-02-11 | Design Specifications
2019-02-25 | PCB DESIGN | [6 empty] | 2019-02-18 | Initial setup of ST board, CubeMX, GIT. \newline Edited Example Code. Made Arduino Test Code.
2019-03-04 | PCB DESIGN |  |  |  | PCB MANUFACTURED |  |  | 2019-02-25 | Layout and PCB design.
2019-03-11 | LED Driver coded |  |  |  | PCB Assembly |  |  | 2019-03-04 | PCB Design and Manufacture.
2019-03-18 | [7 empty] | 2019-03-11 | LED Driver Coding with PCB Tidy Up
2019-03-25 |  |  | v. C of PCB | LED Driver |  |  |  | 2019-03-18 | PCB Tidy Up and Assembly
2019-04-01 | LED / Btn Driver |  |  |  | Btn SPI removed, change of pin | UART & ADC - Tempo control |  | 2019-03-25 | PCB Design Updated and LED Driver Coding
2019-04-08 | Visagie LCD Code |  | Porting BSP |  |  |  |  | 2019-04-01 | Button, UART and ADC (Tempo) Coded
2019-04-15 | Porting BSP | [6 empty] | 2019-04-08 | LCD Coding and STM Audio Driver Added
2019-04-22 | Porting BSP |  | USB Reading |  | BSP Audio and file reading |  |  | 2019-04-15 | Figuring out STM Audio Driver
2019-04-29 | BSP Audio and file reading | [6 empty] | 2019-04-22 | File Reading from USB drive Coding
2019-05-06 | BSP Audio and file reading |  | New Audio Driver |  | Top Panel Manufacture |  |  | 2019-04-29 | File Reading from USB drive Coding and Playing with STM Audio Driver
2019-05-13 | Report Writing | [6 empty] | 2019-05-06 | Changed Audio Driver and Pre-Load Audio Files
2019-05-20 | Report Writing | [6 empty] | 2019-05-13 | Top Panel Manufacture and Report Writing
2019-05-27 | Hand In | [6 empty] | 2019-05-20 | Report Writing
[8 empty] | 2019-05-27 | Report Writing
[8 empty] | 2019-06-03 | Hand In
2019-06-10